First draft outline

Work plan for the intersessional period between POPRC-2 and POPRC-3 for the possible preparation of the risk management evaluation

| Weeks | Date | Activity |
| --- | --- | --- |
| 0 | 10 Nov. 2006 | POPRC sets an ad hoc working group considering the expertise of the Committee members and the possible need of getting invited experts to help the ad hoc working group |
| 1 | 17 Nov. 2006 | Secretariat distributes request for information specified in Annex F (with references to background information) to Parties and observers |
| 11 | 26 Jan. 2007 | Deadline for submissions of information to the Secretariat from Parties and observers |
| 11-19 | 27 Jan–23 March 2007 | Drafter prepares working risk management evaluation |
| 19-24 | 24 March–27 April 2007 | Ad hoc working group considers working risk management evaluation and prepares a first draft risk management evaluation for comments |
| 25-26 | 4 to 11 May 2007 | Secretariat distributes draft risk management evaluation requesting comments from POPRC, Parties and observers |
| 31 | 15 June 2007 | Deadline for submission of comments on the first draft risk management evaluation to the Secretariat from POPRC, Parties and observers |
| 37 | 16 June–27 July 2007 | Ad hoc working group considers comments and prepares a second draft risk management evaluation |
| 38 | 3 Aug. 2007 | Secretariat submits draft risk management evaluation to conference services for editing and translation |
| 45 | 4 Aug. – 24 Sep. 2007 | Editing and translation |
| 45-46 | 25 – 28 Sep. 2006 | Secretariat distributes final draft risk profile in languages |
| 52 | 5–9 Nov. 2007 | POPRC-3 (specific dates to be defined during POPRC-2) |

Definitions, roles and responsibilities

1.	  The term “drafter” would be applied to the person to be designated by the Committee to prepare a working draft risk management evaluation for consideration by the ad hoc working group. The drafter could be the proponent of the chemical, but not necessarily so.

2.   An ad hoc working group would be established by the Committee to review a working draft risk management evaluation and to prepare the draft risk management evaluation.  The Committee may wish to agree that the chair of any given ad hoc working group could declare that group closed and thereby convert it into a drafting group.